## Backlog
ID | Parent ID | Level | Epic | Title | Priority | Optional? | Per-case toggle? | Jurisdiction | Description | Acceptance Criteria | API Endpoints (if any) | DB / Data Model (if any) | UI Components (if any) | Dependencies / Notes
EPIC-1 |  | Epic | Foundations | Auth, Tenancy, Roles, Permissions | P0 | No | No | Global
US1.1 | EPIC-1 | Story | Foundations | Tenant setup + org configuration | P0 | No | No | Global | Tenant-scoped settings drive workflow rules and jurisdiction logic. | Tenant settings persisted; only admins can edit; used by rules engine at runtime. | GET/PUT /tenant/settings | tenants; tenant_settings | Admin settings page
T1.1a | US1.1 | Task | Foundations | Create tenant_settings schema + migration | P0 | No | No | Global |  |  |  | tenant_settings fields for investigation_mode, retention settings, keyword flagging, etc.
T1.1b | US1.1 | Task | Foundations | Implement settings API + validation | P0 | No | No | Global |  |  | GET/PUT /tenant/settings
T1.1c | US1.1 | Task | Foundations | Build settings UI (form + save) | P1 | No | No | Global |  |  |  |  | Admin settings screen
US1.2 | EPIC-1 | Story | Foundations | Authentication + user management | P0 | No | No | Global | Users can log in and be invited/managed within a tenant. | Login works; admins can invite users and assign roles; tenant isolation enforced. | POST /auth/* ; POST /users/invite ; GET/POST /users | users; user_roles | Login, invite user modal, user list
US1.3 | EPIC-1 | Story | Foundations | Role-based access control (RBAC) | P0 | No | No | Global | Enforce permissions at API and UI for roles: ADMIN, INVESTIGATOR, LEGAL, HR, DPO_AUDITOR, VIEWER. | Unauthorized access returns 403; UI hides actions user cannot perform; assignment controls enforced. | RBAC middleware on all endpoints | user_roles; case_assignments | Role assignment UI; guarded routes | Depends on US1.2
US1.4 | EPIC-1 | Story | Foundations | Business-day calendar settings (Belgium deadline calc) | P1 | Yes | No | BE | Tenant-configurable business-day calculator: weekend days, Saturday toggle, public holidays, deadline cut-off. | Deadlines compute consistently; holidays excluded; Saturday rule is configurable; changes are audited. | GET/PUT /tenant/settings ; GET/POST/DELETE /tenant/holidays | tenant_settings (business-day fields); tenant_holidays | Holiday calendar admin UI | Required for Serious Cause Clock feature
T1.4a | US1.4 | Task | Foundations | Implement BusinessDayCalculator service + unit tests | P1 | Yes | No | BE | [5 empty] | Config from tenant_settings + tenant_holidays
EPIC-2 |  | Epic | Core Data Model | Cases, Subjects, Evidence, Tasks, Notes | P0 | No | No | Global
US2.1 | EPIC-2 | Story | Core Data Model | Case object + lifecycle state | P0 | No | No | Global | Create core case model with stage/status enums and subjects. | Case CRUD works; defaults stage=INTAKE and status=OPEN; jurisdiction stored. | POST/GET /cases ; GET /cases/:id ; PUT /cases/:id | cases; case_subjects | Case list + case detail shell
US2.2 | EPIC-2 | Story | Core Data Model | Evidence register (metadata + links) | P0 | No | No | Global | Track evidence items as metadata and references (no telemetry ingestion). | Evidence can be added/edited; required: link OR file upload; export includes evidence register. | POST/GET/PUT /cases/:id/evidence | case_evidence_items | Evidence tab
US2.3 | EPIC-2 | Story | Core Data Model | Case tasks/checklists | P0 | No | No | Global | Task list for playbooks and gates (required_for_stage). | Tasks can be created/assigned/completed; required tasks block stage transitions when configured. | POST/GET/PUT /cases/:id/tasks | case_tasks | Tasks panel
US2.4 | EPIC-2 | Story | Core Data Model | Notes + interview log (append-only) | P1 | No | No | Global | Append-only notes, including interview summaries and decision justification. | Notes are immutable/append-only; keyword flagging runs when enabled. | POST/GET /cases/:id/notes | case_notes | Notes tab / editor
US2.5 | EPIC-2 | Story | Core Data Model | Serious cause toggle + base fields on case | P1 | Yes | Yes | BE | Per-case toggle to enable Belgian 'serious cause' clock; store incident + investigation start dates. | If toggle off: no serious-cause UI or gates. If on: show Serious Cause panel and require decision maker assignment. | POST /cases/:id/serious-cause/enable ; GET /cases/:id/serious-cause | cases.serious_cause_enabled; cases.date_incident_occurred; cases.date_investigation_started | Serious Cause toggle + panel
US2.6 | EPIC-2 | Story | Core Data Model | Serious cause clock record (deadlines + evidence) | P1 | Yes | Yes | BE | Track facts_confirmed_at, computed deadlines, dismissal date, reasons date, delivery method, proof-of-posting, overrides. | facts_confirmed_at only set via workflow action; deadlines computed/stored; overrides are audited and restricted. | POST /cases/:id/actions/submit-findings ; POST /cases/:id/serious-cause/record-dismissal ; POST /cases/:id/serious-cause/record-reasons-sent ; POST /cases/:id/serious-cause/override | case_serious_cause | Serious Cause timeline + inputs | Depends on US1.4
EPIC-3 |  | Epic | Workflow Engine | Stage Transitions + Hard Gates | P0 | No | No | Global
US3.1 | EPIC-3 | Story | Workflow Engine | Workflow transitions with validation | P0 | No | No | Global | Central transition endpoint and validator for allowed transitions and gate checks. | Invalid transitions return 409 with reason codes; UI displays blockers; all transitions audited. | POST /cases/:id/transition | stage/status fields in cases; audit_events | Stage progress UI
US3.2 | EPIC-3 | Story | Workflow Engine | Legitimacy & proportionality gate wizard + mandate record | P0 | No | No | Global | Wizard that captures legal basis and proportionality, generating Investigation Mandate. | Cannot move to CREDENTIALING without approval; mandate is generated, versioned, and auditable. | POST /cases/:id/legitimacy/approve ; POST /cases/:id/documents/INVESTIGATION_MANDATE | case_legitimacy; case_documents | Legitimacy wizard + approve
US3.3 | EPIC-3 | Story | Workflow Engine | Credentialing constraints (licensed vs HR exemption) | P0 | No | No | Global | Investigator profile credentials and lead assignment constraints based on tenant mode and case settings. | Ineligible lead assignment blocked; credential expiry warnings shown; assignments audited. | POST /cases/:id/assign ; GET /users/:id/profile | investigator_profiles; case_assignments | Assignments panel | Depends on US1.3
US3.4 | EPIC-3 | Story | Workflow Engine | Adversarial debate gate (interview/response required) | P1 | No | No | Global | Track invitation/interview and subject response; gate transition to DECISION. | Cannot move to DECISION without recorded response or LEGAL-approved exception; letters generated from template. | POST /cases/:id/adversarial/update ; POST /cases/:id/documents/INTERVIEW_INVITATION | case_adversarial | Adversarial step UI
US3.5 | EPIC-3 | Story | Workflow Engine | Action: Submit Findings to Decision Maker (starts 3-day clock) | P1 | Yes | Yes | BE | Dedicated action logs when competent authority receives confirmed facts; starts dismissal deadline countdown. | facts_confirmed_at set only via this action; confirmation modal shown; deadline_dismissal computed; audit event written. | POST /cases/:id/actions/submit-findings | case_serious_cause.facts_confirmed_at; case_serious_cause.deadline_dismissal_at; audit_events | Submit Findings button + modal | Depends on US2.6
US3.6 | EPIC-3 | Story | Workflow Engine | Active guardrails for deadline expiry + acknowledgements | P1 | Yes | Yes | BE | If deadlines are missed, system shows persistent state and requires LEGAL/ADMIN acknowledgment for relevant actions. | Missed deadlines trigger alerts and audit events; dismissal/reasons path cannot be completed without acknowledgment; exceptions are logged. | POST /cases/:id/serious-cause/acknowledge-missed (optional) | audit_events; case_serious_cause.override fields | Deadline banner + acknowledgment dialog
EPIC-4 |  | Epic | Playbooks | Template-driven tasks & evidence suggestions | P1 | No | No | Global
US4.1 | EPIC-4 | Story | Playbooks | Playbook library + apply to case (3 playbooks MVP) | P1 | No | No | Global | Apply playbooks (DATA_EXFIL, FRAUD, SABOTAGE) to auto-create tasks and evidence suggestions. | Applying playbook creates tasks/suggestions; no duplicates on reapply; actions audited. | POST /cases/:id/apply-playbook | playbooks (JSON in code or table); case_tasks | Apply playbook UI
US4.2 | EPIC-4 | Story | Playbooks | Evidence checklist suggestions UX | P2 | No | No | Global | Suggested evidence sidebar; one click converts suggestion into evidence item draft. | Suggestion can be converted into evidence item; users can dismiss suggestions. |  |  | Suggestions sidebar | Depends on US2.2
EPIC-5 |  | Epic | Documents & Export | Template generation, versioning, export pack | P0 | No | No | Global
US5.1 | EPIC-5 | Story | Documents & Export | Document template engine (PDF/DOCX) | P0 | No | No | Global | Generate documents with versioning and immutable storage URIs. | Docs generated per case and type; versioned; include timestamps and case ID; audited. | POST /cases/:id/documents/:type ; GET /cases/:id/documents | case_documents | Documents tab
US5.2 | EPIC-5 | Story | Documents & Export | One-click Case Export Pack (ZIP) | P1 | No | No | Global | Bundle PDFs + evidence register + timeline into downloadable ZIP. | Export only includes permitted content; export is audited; ZIP is generated server-side. | GET /cases/:id/export | audit_events | Export button | Depends on US5.1, US6.1
US5.3 | EPIC-5 | Story | Documents & Export | Dismissal reasons letter template from 'Proven Facts' (serious cause) | P1 | Yes | Yes | BE | Generate dismissal reasons letter using canonical 'Proven Facts' content, with versioning and change controls. | Letter pulls exact proven facts; editing facts after generation requires LEGAL approval and creates new doc version; audited. | POST /cases/:id/documents/DISMISSAL_REASONS_LETTER | case_notes(note_type=PROVEN_FACTS) OR case_findings; case_documents | Proven Facts editor + generate letter | Depends on US2.4, US2.6
US5.4 | EPIC-5 | Story | Documents & Export | Proof-of-posting upload for registered mail (optional enforcement) | P2 | Yes | Yes | BE | If delivery method is REGISTERED_MAIL, require receipt upload before marking reasons as notified. | Receipt is required only for registered mail method; state cannot progress without upload; audited. | POST /cases/:id/serious-cause/record-reasons-sent | case_serious_cause.registered_mail_receipt_uri | Upload control on Serious Cause panel
EPIC-6 |  | Epic | Audit & Prohibited Data | Audit trail + keyword flagging guardrails | P0 | No | No | Global
US6.1 | EPIC-6 | Story | Audit & Prohibited Data | Immutable audit log | P0 | No | No | Global | Append-only audit events for key actions (transitions, assignments, exports, settings changes). | All critical actions write audit events; records are append-only; searchable by case/actor. | Internal logging helper; GET /audit?case_id=... | audit_events | Audit tab (optional MVP)
US6.2 | EPIC-6 | Story | Audit & Prohibited Data | Prohibited data keyword flagging (MVP) | P1 | No | No | Global | Keyword scan notes/interview summaries for sensitive categories; create flags for LEGAL review. | Matches display warnings before final docs; flags require resolution; all actions audited. | POST /cases/:id/notes (scan) ; GET/PUT /cases/:id/flags | content_flags; keyword_lists | Flags panel + warnings
US6.3 | EPIC-6 | Story | Audit & Prohibited Data | Add serious-cause audit event types | P2 | Yes | Yes | BE | Add audit event types for clock start/stop, missed deadlines, overrides, notifications. | Serious-cause state changes are fully auditable with actor + timestamp + reason. |  | audit_events (event_type enum/strings) |  | Depends on US2.6, US3.5
EPIC-7 |  | Epic | Retention & Erasure | No-sanction erasure workflow + certificate | P0 | No | No | Global
US7.1 | EPIC-7 | Story | Retention & Erasure | Decision & outcome model | P1 | No | No | Global | Record case outcomes and decision summary; required before closure. | Outcome required; decision recorded with actor+timestamp; audited. | POST /cases/:id/decision | case_outcomes | Decision step UI
US7.2 | EPIC-7 | Story | Retention & Erasure | Erasure trigger + certificate (no sanction) | P0 | No | No | Global | If outcome is NO_SANCTION, trigger erasure timer and generate certificate of destruction on execution. | Only LEGAL/ADMIN can approve erasure; job executes after retention period; certificate generated; status=ERASED; audited. | POST /cases/:id/erasure/approve ; POST /cases/:id/erasure/execute | cases.status; erasure_jobs; case_documents | Erasure workflow UI | Depends on US5.1, US6.1
EPIC-8 |  | Epic | Jurisdiction Guardrails | PIA-aware behavior for Belgium cases | P1 | No | No | Global
US8.1 | EPIC-8 | Story | Jurisdiction Guardrails | Jurisdiction banner + stricter rules for Belgium cases | P1 | No | No | Global | When case jurisdiction=BE, show persistent banner and enforce full PIA workflow gates. | BE cases cannot bypass mandated gates; banner displayed; audited when jurisdiction set/changed. |  | cases.jurisdiction | Banner on case header
US8.2 | EPIC-8 | Story | Jurisdiction Guardrails | User access restriction by 'BE authorized' flag (lite geo-routing) | P2 | No | No | Global | Optional authorization flag: only BE-authorized users can be assigned to BE cases. | Assignment to BE case blocked if user not authorized; shows clear error; audited. |  | users.is_be_authorized (or allowed_jurisdictions[]) | User profile field + assignment validation | Depends on US1.3
EPIC-9 |  | Epic | Dashboards & Notifications | Compliance + operational metrics | P1 | No | No | Global
US9.1 | EPIC-9 | Story | Dashboards & Notifications | Basic operational dashboard | P1 | No | No | Global | Cases by stage/status; time in stage; compliance completion rates. | Admin sees tenant-wide metrics; DPO_AUDITOR sees stats only; no case identities in auditor view. | GET /dashboard |  | Dashboard page | Depends on US6.1
US9.2 | EPIC-9 | Story | Dashboards & Notifications | Systematic drift monitoring (HR exemption guardrail) | P2 | No | No | Global | Rolling window metrics to warn when HR exemption posture may be drifting into systematic investigations. | Threshold alerts show to ADMIN/LEGAL; alerts audited; thresholds configurable. |  | Derived metrics; optional table for alerts | Dashboard alert banner | Depends on US1.1, US2.1
US9.3 | EPIC-9 | Story | Dashboards & Notifications | Serious-cause countdown widget | P1 | Yes | Yes | BE | Countdown on HR/Legal dashboard after facts_confirmed_at; color states; missed state. | Widget shows only for serious_cause_enabled cases; correct remaining time; updates at least hourly. |  |  | Dashboard card + case list badges | Depends on US2.6, US3.5
US9.4 | EPIC-9 | Story | Dashboards & Notifications | Notifications for serious-cause milestones (in-app/email) | P2 | Yes | Yes | BE | Notify decision maker/legal at clock start; reminders 48h/24h/6h; missed deadline alerts. | Notifications can be toggled; sent events are audited; scheduler runs hourly. |  | notifications; audit_events | Notification center | Depends on US9.3
EPIC-10 |  | Epic | Quality & Security | Security baseline + automated tests | P0 | No | No | Global
US10.1 | EPIC-10 | Story | Quality & Security | Security baseline | P0 | No | No | Global | Input validation, output encoding, file upload scanning (if enabled), rate limiting, tenant isolation. | No cross-tenant access; security checks in place; basic OWASP measures applied. |  |  |  | Applies across epics
US10.2 | EPIC-10 | Story | Quality & Security | Automated tests | P1 | No | No | Global | Unit tests for validator + business day calc; integration tests for RBAC + transitions; doc generation snapshots. | CI blocks merges on critical validator failures; test suite covers deadline edge cases. |  |  |  | Depends on core validators and BusinessDayCalculator (if used)
US1.5 | EPIC-1 | Story | Foundations | Secure reporter portal (anonymous 2-way) | P1 | No | No | Global | Anonymous reporter portal with secure key to allow follow-up Q&A without revealing identity; links to case. | Reporter can re-enter with secure key; investigator questions/responses are captured and linked to the case. | POST/GET /whistleblow/portal (integration stub) | case_external_reports (external_report_id, reporter_key_ref) | External portal + case link panel | Depends on whistleblow tool integration.
US1.6 | EPIC-1 | Story | Foundations | VIP / highly sensitive case lockdown | P1 | No | Yes | Global | Restrict visibility to assigned investigator/external counsel; redact subject names in dashboards for VIP cases. | VIP cases hidden from general lists; only assigned users can view; dashboards show redacted subject labels. | PATCH /cases/:id (vip_flag) | cases.vip_flag (bool), case_access_overrides | VIP toggle + restricted case badge | Depends on RBAC + assignment model.
US2.7 | EPIC-2 | Story | Core Data Model | Case linking (duplicate/related) | P2 | No | No | Global | Link cases as duplicate/related; allow master-child rollup to avoid duplicated investigations. | User can link/unlink cases; master case displays linked cases; closing master can optionally close children. | POST/DELETE /cases/:id/links | case_links (case_id, linked_case_id, relation_type) | Related cases panel
US2.8 | EPIC-2 | Story | Core Data Model | Silent legal hold generator | P1 | Yes | Yes | Global | Generate password-protected preservation instruction for trusted IT contact with COI check. | Hold instruction PDF generated; COI check enforced; audit trail captured. | POST /cases/:id/legal-hold | case_legal_holds | Legal hold generator UI | Requires COI check and document engine.
US2.9 | EPIC-2 | Story | Core Data Model | Immutable evidence hashing | P1 | No | No | Global | Store cryptographic hash for evidence artifacts to prevent tampering. | Evidence records include hash; hash verified on export. | POST /cases/:id/evidence (hash field) | case_evidence_items.evidence_hash | Evidence register hash field | Requires file attachment support or hash upload.
US2.10 | EPIC-2 | Story | Core Data Model | External report metadata linkage | P2 | Yes | No | Global | Store external whistleblow report identifiers to link cases with external portal. | Case stores external report ID and channel reference; shown in case header. | PATCH /cases/:id (external_report_id) | cases.external_report_id, cases.reporter_channel_id | External report link panel | Depends on whistleblow tool integration.
US3.7 | EPIC-3 | Story | Workflow Engine | Conflict of interest check (investigator vs subject) | P1 | No | No | Global | Block investigator assignment if investigator matches subject or subject manager. | System warns/blocks assignment; requires override justification + audit log. | POST /cases/:id/gates/credentialing (COI check) | case_gate_records + subject roster | Credentialing COI warning modal | Requires subject list and user directory.
US3.8 | EPIC-3 | Story | Workflow Engine | Role separation (investigator ≠ decision maker) | P1 | No | No | Global | Prevent decision maker from being the same as investigator to ensure procedural fairness. | Decision step blocked if decision maker matches investigator; override requires legal sign-off. | POST /cases/:id/decision (role separation check) | case_outcomes.decided_by, case_metadata.decision_maker | Decision form validation warning | Depends on credentialing data.
US5.5 | EPIC-5 | Story | Documents & Export | DSAR redaction tool | P2 | Yes | No | Global | Redact witness names and sensitive content before DSAR export. | User can preview and redact export; redaction logged in audit trail. | POST /cases/:id/export/redact | case_documents.redaction_log | Export preview + redaction UI | Requires export pack and document viewer.
US7.3 | EPIC-7 | Story | Retention & Erasure | Retaliation monitoring task | P2 | Yes | Yes | EU | Auto-schedule a follow-up task 3 months post-closure to check for retaliation. | On close, task created with due date + reminder; task visible in case tasks. | POST /cases/:id/retaliation-monitor | case_tasks (type=retaliation_check) | Task badge + reminder banner | Depends on closure workflow.
US7.4 | EPIC-7 | Story | Retention & Erasure | Remediation export (assessment handshake) | P2 | Yes | Yes | Global | On proven cases, export problem statement to Assessment/Recommendations module. | Closure prompts problem statement; export generates JSON/CSV for assessment intake. | POST /cases/:id/remediation-export | case_metadata.remediation_statement | Closure prompt + export button | Depends on assessment integration.
US8.3 | EPIC-8 | Story | Jurisdiction Guardrails | Jurisdiction rules config (JSON) | P1 | No | No | Global | Store jurisdiction rules in tenant settings to avoid hard-coded logic. | Rules can be edited in settings; API returns rule set by tenant. | GET/PUT /tenant/settings | tenant_settings.jurisdiction_rules (json) | Jurisdiction rules editor | Foundation for NL/LU/IE support.
US8.4 | EPIC-8 | Story | Jurisdiction Guardrails | Jurisdiction validator service | P1 | No | No | Global | Rule-driven warnings/blocks for stage transitions and document generation. | Validator blocks/ warns based on tenant rules; no hard-coded country checks. | Validator hooks in /cases/:id/stage and /documents | Uses tenant_settings.jurisdiction_rules | Warning modal + banner | Depends on US8.3.

## Config & Rules
Category | Key | Value/Description
Workflow | Stages | INTAKE → LEGITIMACY_GATE → CREDENTIALING → INVESTIGATION → ADVERSARIAL_DEBATE → DECISION → CLOSURE
Workflow | Statuses | OPEN, ON_HOLD, CLOSED, ERASURE_PENDING, ERASED
RBAC | Roles | ADMIN, INVESTIGATOR, LEGAL, HR, DPO_AUDITOR, VIEWER
BE Optional | Serious Cause Toggle | Per-case toggle enables Belgian double 3-day rule guardrails (facts_confirmed_at → dismissal deadline; dismissal → reasons deadline).
Calendar | BusinessDayCalculator | Configurable weekend days, Saturday on/off, holiday list per jurisdiction; computes absolute deadline timestamps.
Documents | MVP Document Types | INVESTIGATION_MANDATE, INTERVIEW_INVITATION, DECISION_MEMO, CLOSURE_REPORT, CERTIFICATE_OF_DESTRUCTION, (optional) DISMISSAL_REASONS_LETTER
Out-of-scope | Telemetry | No SIEM/DLP/UEBA ingestion; evidence stored as metadata/links only.
Jurisdiction Engine | jurisdiction_rules | JSON rules by country (deadlines, warnings, required steps). Stored in tenant settings.

## Glossary
Term | Definition
Jurisdiction | Country/region whose legal workflow constraints apply (e.g., BE for Belgium).
PIA/PIA module | Process impact / procedural compliance layer wrapping human investigation steps (not a monitoring tool).
Serious cause (BE) | Urgent dismissal path with strict working-day deadlines for dismissal and notification of reasons.
facts_confirmed_at | Timestamp when competent authority receives confirmed facts; starts dismissal deadline clock when serious cause is enabled.
Adversarial debate | Right-to-be-heard step; interview/response must be recorded or exception approved by legal.
Erasure (no sanction) | Deletion/anonymization workflow triggered when outcome is NO_SANCTION; produces a certificate of destruction.