## Action Plan
ID | Priority | Phase | Workstream | Deliverable | What to do (detailed) | Why (business) | Why (technical) | Where (files/modules) | Data/Schema changes | API changes | UI changes | Acceptance criteria (definition of done) | Dependencies | Effort (S/M/L) | Notes | Column1 | Status
P0-01 | P0 | Pilot Foundation | Adaptive UX | Reachable-path sidebar (Gatekeeper-aware) | Render sidebar from server-provided reachable question list only. Hide questions behind Gatekeepers until unlocked. Provide optional 'locked' state with tooltip explaining why. | Prevents confusion and drop-off; makes the 'neuro-adaptive' promise feel real. | Avoids client-side re-implementation of branching rules; single source of truth on server. | assessment.html (sidebar render), services/engines (context builder) | None | Ensure /assessment/{id}/context returns reachable_path + reasons (locked_by, gatekeeper_qid) | Collapsible/stretchable sidebar + reachable list + optional locked tooltips | In any domain: user sees only relevant/reachable questions; no irrelevant list; no broken navigation. | P0-03, P0-04 | M | Make locked tooltip text consistent with your methodology language (Foundational gate, etc.). | P0-01,P0,Pilot Foundation,Adaptive UX,Reachable-path sidebar (Gatekeeper-aware),Render sidebar from server-provided reachable question list only. Hide questions behind Gatekeepers until unlocked. Provide optional 'locked' state with tooltip explaining why.,Prevents confusion and drop-off; makes the 'neuro-adaptive' promise feel real.,Avoids client-side re-implementation of branching rules; single source of truth on server.,assessment.html (sidebar render), services/engines (context builder),None,Ensure /assessment/{id}/context returns reachable_path + reasons (locked_by, gatekeeper_qid),Collapsible/stretchable sidebar + reachable list + optional locked tooltips,In any domain: user sees only relevant/reachable questions; no irrelevant list; no broken navigation.,P0-03, P0-04,M,Make locked tooltip text consistent with your methodology language (Foundational gate, etc.). | Not started
P0-02 | P0 | Pilot Foundation | Session/Resumption | Server-side resume handshake | On load and on 'Resume', rebuild userResponses and navigation state from DB (fact_responses) using access token / assessment key; localStorage becomes a cache only. | Users can switch devices/browsers; supports auditors and multi-stakeholder completion workflows. | Prevents state desync and client-only corruption; improves audit defensibility. | assessment.html init(), main.py resume/context routes, repositories/services | Ensure fact_responses stores question_id/a_id/score and optional metadata (origin, evidence_confidence) | GET /assessments/resume/{assessment_id} (or /assessment/{id}/context) returns responses + next_best_qid | Welcome page 'Enter' always calls server; dashboard shows 'Continue' CTA | Refresh browser: progress persists; resume restores answers + correct next question without localStorage. | Database working; auth mode set for dev | M | Keep DEV_AUTH_DISABLED for alpha; later replace with JWT/tenant auth. | P0-02,P0,Pilot Foundation,Session/Resumption,Server-side resume handshake,On load and on 'Resume', rebuild userResponses and navigation state from DB (fact_responses) using access token / assessment key; localStorage becomes a cache only.,Users can switch devices/browsers; supports auditors and multi-stakeholder completion workflows.,Prevents state desync and client-only corruption; improves audit defensibility.,assessment.html init(), main.py resume/context routes, repositories/services,Ensure fact_responses stores question_id/a_id/score and optional metadata (origin, evidence_confidence),GET /assessments/resume/{assessment_id} (or /assessment/{id}/context) returns responses + next_best_qid,Welcome page 'Enter' always calls server; dashboard shows 'Continue' CTA,Refresh browser: progress persists; resume restores answers + correct next question without localStorage.,Database working; auth mode set for dev,M,Keep DEV_AUTH_DISABLED for alpha; later replace with JWT/tenant auth. | Implemented
P0-03 | P0 | Pilot Foundation | Navigation | Next-best-question guidance (stop/return) | Compute a deterministic 'next_best_qid' and 'next_best_reason' on server: prioritize (1) marked-for-review, (2) deferred, (3) next unanswered reachable. Add a small 'Continue' card on dashboard. | Directly addresses user dropout and improves completion rates; makes product feel guided. | Centralizes routing and prevents UI guessing; reduces 'random jumps'. | services.py (assessment context), engines.py (routing helper), assessment.html dashboard | Optionally store last_seen_qid per assessment for analytics; not required | Include next_best_qid in context response | Dashboard card: Continue / Review / Deferred sections | If user exits mid-question: reopening takes them to the most relevant next step with explanation. | P0-02 | M | Also log routing decisions for later tuning. | P0-03,P0,Pilot Foundation,Navigation,Next-best-question guidance (stop/return),Compute a deterministic 'next_best_qid' and 'next_best_reason' on server: prioritize (1) marked-for-review, (2) deferred, (3) next unanswered reachable. Add a small 'Continue' card on dashboard.,Directly addresses user dropout and improves completion rates; makes product feel guided.,Centralizes routing and prevents UI guessing; reduces 'random jumps'.,services.py (assessment context), engines.py (routing helper), assessment.html dashboard,Optionally store last_seen_qid per assessment for analytics; not required,Include next_best_qid in context response,Dashboard card: Continue / Review / Deferred sections,If user exits mid-question: reopening takes them to the most relevant next step with explanation.,P0-02,M,Also log routing decisions for later tuning. | Not started
P0-04 | P0 | Pilot Foundation | Security | Non-guessable assessment IDs | Stop client-generated short IDs. Create assessments server-side with UUID/ULID. Provide a shareable 'assessment key' that is long, unguessable, and can be revoked later. | Prevents accidental data exposure; increases enterprise trust. | Eliminates enumeration risk; enables multi-tenant future. | assessment.html (new assessment), main.py create assessment endpoint, auth.py | Add assessments table fields: assessment_id (ulid/uuid), created_at, mode, override_depth flag | POST /assessments to create; return id + token (dev mode still frictionless) | Replace ID input flow: 'Start new' calls server; optionally allow custom label (not name). | Attempting to guess IDs yields 404/401; IDs are high entropy; new flow works in dev. | P0-02 | S | In alpha: you can still display the ID clearly and offer copy button. | P0-04,P0,Pilot Foundation,Security,Non-guessable assessment IDs,Stop client-generated short IDs. Create assessments server-side with UUID/ULID. Provide a shareable 'assessment key' that is long, unguessable, and can be revoked later.,Prevents accidental data exposure; increases enterprise trust.,Eliminates enumeration risk; enables multi-tenant future.,assessment.html (new assessment), main.py create assessment endpoint, auth.py,Add assessments table fields: assessment_id (ulid/uuid), created_at, mode, override_depth flag,POST /assessments to create; return id + token (dev mode still frictionless),Replace ID input flow: 'Start new' calls server; optionally allow custom label (not name).,Attempting to guess IDs yields 404/401; IDs are high entropy; new flow works in dev.,P0-02,S,In alpha: you can still display the ID clearly and offer copy button. | Not started
P0-05 | P0 | Pilot Foundation | Scoring Core | Declared vs Verified scoring separation | Classify questions into Declared vs Verified (based on tier/metadata). Compute both sets separately per axis & domain; compute SI gap. Store in report snapshot. | Creates C-level defensibility; reveals paper programs vs reality; drives program roadmap urgency. | Implements core IRMMF v6.1 methodology; avoids averaging away contradictions. | engines.py (scoring), services.py (analysis), schemas.py (analysis payload) | Add per-response: layer (declared/verified) or infer from question.tier; store in snapshots. | GET /responses/analysis/{assessment_id} returns declared_vector, verified_vector, gap_vector | Results page: show SI gap & explain meaning; add 'confidence' overlay later | A scenario with high declared + low verified triggers Paper Dragon SI gap flag; results clearly show both. | P0-06 | M | Keep rules in one engine module and version it. | P0-05,P0,Pilot Foundation,Scoring Core,Declared vs Verified scoring separation,Classify questions into Declared vs Verified (based on tier/metadata). Compute both sets separately per axis & domain; compute SI gap. Store in report snapshot.,Creates C-level defensibility; reveals paper programs vs reality; drives program roadmap urgency.,Implements core IRMMF v6.1 methodology; avoids averaging away contradictions.,engines.py (scoring), services.py (analysis), schemas.py (analysis payload),Add per-response: layer (declared/verified) or infer from question.tier; store in snapshots.,GET /responses/analysis/{assessment_id} returns declared_vector, verified_vector, gap_vector,Results page: show SI gap & explain meaning; add 'confidence' overlay later,A scenario with high declared + low verified triggers Paper Dragon SI gap flag; results clearly show both.,P0-06,M,Keep rules in one engine module and version it. | Not started
P0-06 | P0 | Pilot Foundation | Scoring Core | Circuit breakers (Fatigue & Shadow caps) + Alpha penalty | After base scoring, apply: (a) Fatigue cap (H low caps R), (b) Shadow cap (V low caps G), (c) Alpha penalty: if cw>1.2 and response<th => multiply by 0.3 (or as specified). | Prevents greenwashing; surfaces high-risk archetypes; increases trust with auditors. | Aligns output with IRMMF v6.1 'hard-coded' logic rules. | engines.py scoring post-processing; main.py analysis endpoint | None | None (analysis payload includes flags indicating caps applied) | Results: show 'caps applied' badges and affected axes | Given inputs that satisfy cap conditions, output is capped and flags show why. | P0-05 | M | Make cap thresholds configurable by engine version. | P0-06,P0,Pilot Foundation,Scoring Core,Circuit breakers (Fatigue & Shadow caps) + Alpha penalty,After base scoring, apply: (a) Fatigue cap (H low caps R), (b) Shadow cap (V low caps G), (c) Alpha penalty: if cw>1.2 and response<th => multiply by 0.3 (or as specified).,Prevents greenwashing; surfaces high-risk archetypes; increases trust with auditors.,Aligns output with IRMMF v6.1 'hard-coded' logic rules.,engines.py scoring post-processing; main.py analysis endpoint,None,None (analysis payload includes flags indicating caps applied),Results: show 'caps applied' badges and affected axes,Given inputs that satisfy cap conditions, output is capped and flags show why.,P0-05,M,Make cap thresholds configurable by engine version. | Not started
P0-07 | P0 | Pilot Foundation | Evidence (No Upload) | Evidence attestation + challenge micro-questions | For relevant questions: ask 'Do you have evidence?' then 3–6 micro-questions to assess evidence maturity (freshness, scope, independence, sampling, traceability). No file uploads. Store structured JSON and compute evidence_confidence. | Avoids NDA/file friction; increases credibility; reduces overstatement risk. | Adds a confidence signal without handling documents; supports future connectors. | assessment.html (option expand / dropdown), schemas.py, models.py (response metadata), engines.py (confidence) | Add columns/JSON: fact_responses.evidence (jsonb), evidence_confidence (float), evidence_policy_id ref | Update POST /responses/submit to accept evidence payload | Inline dropdown on certain answers; quick 30–60s flow; optional notes field | Users can complete without uploads; evidence confidence computed and shown in report appendix. | P0-05 | M | Implement via templates keyed by evidence_policy_id, but allow per-question overrides. | P0-07,P0,Pilot Foundation,Evidence (No Upload),Evidence attestation + challenge micro-questions,For relevant questions: ask 'Do you have evidence?' then 3–6 micro-questions to assess evidence maturity (freshness, scope, independence, sampling, traceability). No file uploads. Store structured JSON and compute evidence_confidence.,Avoids NDA/file friction; increases credibility; reduces overstatement risk.,Adds a confidence signal without handling documents; supports future connectors.,assessment.html (option expand / dropdown), schemas.py, models.py (response metadata), engines.py (confidence),Add columns/JSON: fact_responses.evidence (jsonb), evidence_confidence (float), evidence_policy_id ref,Update POST /responses/submit to accept evidence payload,Inline dropdown on certain answers; quick 30–60s flow; optional notes field,Users can complete without uploads; evidence confidence computed and shown in report appendix.,P0-05,M,Implement via templates keyed by evidence_policy_id, but allow per-question overrides. | Not started
P0-08 | P0 | Pilot Foundation | UX Controls | Mark for review + overview | Add 'Mark for review' button (separate from Defer). Show a dashboard section listing review items; prioritize these in next-best routing. | Supports audit workflows and multi-stakeholder validation. | Adds separate state bucket; improves routing logic. | assessment.html, services.py context builder | Store review marks in fact_responses metadata or a separate table | Include marked_for_review list in context response | Add button + dashboard list + counts | Marked items persist server-side; appear on dashboard; routing prioritizes them. | P0-02, P0-03 | S | You can later add 'assign to role' for review items. | P0-08,P0,Pilot Foundation,UX Controls,Mark for review + overview,Add 'Mark for review' button (separate from Defer). Show a dashboard section listing review items; prioritize these in next-best routing.,Supports audit workflows and multi-stakeholder validation.,Adds separate state bucket; improves routing logic.,assessment.html, services.py context builder,Store review marks in fact_responses metadata or a separate table,Include marked_for_review list in context response,Add button + dashboard list + counts,Marked items persist server-side; appear on dashboard; routing prioritizes them.,P0-02, P0-03,S,You can later add 'assign to role' for review items. | Not started
P0-09 | P0 | Pilot Foundation | Performance | Add core indexes for heavy filtering | Ensure indexes exist on dim_questions(domain,tier), dim_answers(question_id), fact_responses(assessment_id,q_id), etc. | Faster UX; critical when multiple users/tenants; avoids lag that kills completion. | Prevents full-table scans; lowers DB load. | database.py startup ensure_indexes or migrations | SQL indexes only | None | None | Queries for /questions/all and /context stay fast (<300ms locally; <1s in pilot infra). | DB schema stable | S | Move to Alembic migrations once stable. | P0-09,P0,Pilot Foundation,Performance,Add core indexes for heavy filtering,Ensure indexes exist on dim_questions(domain,tier), dim_answers(question_id), fact_responses(assessment_id,q_id), etc.,Faster UX; critical when multiple users/tenants; avoids lag that kills completion.,Prevents full-table scans; lowers DB load.,database.py startup ensure_indexes or migrations,SQL indexes only,None,None,Queries for /questions/all and /context stay fast (<300ms locally; <1s in pilot infra).,DB schema stable,S,Move to Alembic migrations once stable. | Not started
P1-01 | P1 | Enterprise Core | Adaptive Logic | Override depth toggle (alpha) with origin tagging | Add UI toggle 'Explore deeper questions' and store override_depth at assessment level. Tag each response origin=adaptive¦override. Default scoring excludes override answers from benchmarks; include in appendix. | Lets CISOs/auditors go deeper without breaking adaptive promise; supports small-but-mature orgs. | Prevents override answers from contaminating adaptive path analytics and benchmarks. | assessment.html (toggle), services.py (routing), models.py (assessment, response metadata) | assessments.override_depth bool; fact_responses.origin enum/text | POST /assessments, GET /context includes override state | Toggle + banner explaining implications; lock icon changes | With override off, deep questions hidden. With override on, they appear and are labeled 'override'. | P0-01, P0-05 | M | Also record why user enabled override (optional short selection). | P1-01,P1,Enterprise Core,Adaptive Logic,Override depth toggle (alpha) with origin tagging,Add UI toggle 'Explore deeper questions' and store override_depth at assessment level. Tag each response origin=adaptive¦override. Default scoring excludes override answers from benchmarks; include in appendix.,Lets CISOs/auditors go deeper without breaking adaptive promise; supports small-but-mature orgs.,Prevents override answers from contaminating adaptive path analytics and benchmarks.,assessment.html (toggle), services.py (routing), models.py (assessment, response metadata),assessments.override_depth bool; fact_responses.origin enum/text,POST /assessments, GET /context includes override state,Toggle + banner explaining implications; lock icon changes,With override off, deep questions hidden. With override on, they appear and are labeled 'override'.,P0-01, P0-05,M,Also record why user enabled override (optional short selection). | Not started
P1-02 | P1 | Enterprise Core | Archetypes | Expanded archetype engine (single output) + future-proofing | Implement archetype scoring rules per axis patterns + SI gaps. Output one primary archetype + rationale bullets. Store runner-up and confidence internally for future. | Creates a compelling C-level story; supports advisory upsell and program design. | Aligns classification with methodology; avoids misleading labels. | engines.py (archetype rules), services.py (analysis), schemas.py (report) | report_snapshots store archetype_details JSON | None | Results page shows archetype card + 'why' bullets | Given known test profiles, archetype matches expected; rationale is explainable and traceable. | P0-05, P0-06 | L | Start with ~6–10 archetypes; expand over time. | P1-02,P1,Enterprise Core,Archetypes,Expanded archetype engine (single output) + future-proofing,Implement archetype scoring rules per axis patterns + SI gaps. Output one primary archetype + rationale bullets. Store runner-up and confidence internally for future.,Creates a compelling C-level story; supports advisory upsell and program design.,Aligns classification with methodology; avoids misleading labels.,engines.py (archetype rules), services.py (analysis), schemas.py (report),report_snapshots store archetype_details JSON,None,Results page shows archetype card + 'why' bullets,Given known test profiles, archetype matches expected; rationale is explainable and traceable.,P0-05, P0-06,L,Start with ~6–10 archetypes; expand over time. | Not started
P1-03 | P1 | Enterprise Core | Recommendations | Recommendation databank (archetype + domain + axis) | Build a recommendation library keyed by (archetype, low axes, high gaps, fracture tags). Output top 5 prioritized actions with sequencing (30/60/90 days). | Turns assessment into an IRM program blueprint; drives advisory engagement. | Decouples content from code; allows updates without redeploying core scoring. | services.py (recommendations), new data file/table rec_library, report generation | New table or JSON file with versioning; store which recs were shown in snapshot | Add /recommendations endpoint (optional) | Results page + export: 'Top actions' | Report always produces actionable plan with owners/timelines; consistent across runs via snapshot. | P1-02 | L | Authoring effort: start with 30–60 core recommendations. | P1-03,P1,Enterprise Core,Recommendations,Recommendation databank (archetype + domain + axis),Build a recommendation library keyed by (archetype, low axes, high gaps, fracture tags). Output top 5 prioritized actions with sequencing (30/60/90 days).,Turns assessment into an IRM program blueprint; drives advisory engagement.,Decouples content from code; allows updates without redeploying core scoring.,services.py (recommendations), new data file/table rec_library, report generation,New table or JSON file with versioning; store which recs were shown in snapshot,Add /recommendations endpoint (optional),Results page + export: 'Top actions',Report always produces actionable plan with owners/timelines; consistent across runs via snapshot.,P1-02,L,Authoring effort: start with 30–60 core recommendations. | Not started
P1-04 | P1 | Enterprise Core | Scoring Model | Domain + Axis scoring combined views | Compute axis scores using question axis1/axis2 weights; compute domain rollups separately. Present both: Axis radar + Domain heatmap/table. | Executives want domain view; technical teams want axis signal; reduces misinterpretation. | Fixes current conflation of domain vs axis; respects question weighting. | engines.py scoring, schemas.py output, assessment.html results | None | None | Results tabs: Axis view / Domain view / Role view | Axis scores change appropriately when dual-axis weights are adjusted; domain rollups stable and explainable. | P0-05 | M | Keep weighting in data (Excel) so analysts can tune without code. | P1-04,P1,Enterprise Core,Scoring Model,Domain + Axis scoring combined views,Compute axis scores using question axis1/axis2 weights; compute domain rollups separately. Present both: Axis radar + Domain heatmap/table.,Executives want domain view; technical teams want axis signal; reduces misinterpretation.,Fixes current conflation of domain vs axis; respects question weighting.,engines.py scoring, schemas.py output, assessment.html results,None,None,Results tabs: Axis view / Domain view / Role view,Axis scores change appropriately when dual-axis weights are adjusted; domain rollups stable and explainable.,P0-05,M,Keep weighting in data (Excel) so analysts can tune without code. | Not started
P1-05 | P1 | Enterprise Core | Intake | Light, anonymous intake for benchmarking + routing (no company name) | Implement minimal intake (industry bucket, region bucket, size band optional, regulated flags). Use it for benchmark tags and initial depth suggestion. Do not block small-but-mature: allow early maturity signals to promote depth. | Reduces friction, supports anonymity, enables benchmarking and tailored flow. | Enables cohort analytics; supports future external benchmarks. | index.html / intake UI, services.py intake engine, models.py intake responses | Store benchmark_tags JSON in assessment or snapshot | POST /intake/submit, GET /intake/options | Simple intake wizard (5–10 items), optional | Assessment can proceed without company name; benchmark tags captured; depth suggestion computed. | P0-02, P1-01 | M | Later: allow client to add name only to exported report. | P1-05,P1,Enterprise Core,Intake,Light, anonymous intake for benchmarking + routing (no company name),Implement minimal intake (industry bucket, region bucket, size band optional, regulated flags). Use it for benchmark tags and initial depth suggestion. Do not block small-but-mature: allow early maturity signals to promote depth.,Reduces friction, supports anonymity, enables benchmarking and tailored flow.,Enables cohort analytics; supports future external benchmarks.,index.html / intake UI, services.py intake engine, models.py intake responses,Store benchmark_tags JSON in assessment or snapshot,POST /intake/submit, GET /intake/options,Simple intake wizard (5–10 items), optional,Assessment can proceed without company name; benchmark tags captured; depth suggestion computed.,P0-02, P1-01,M,Later: allow client to add name only to exported report. | Not started
P1-06 | P1 | Enterprise Core | UX / IA | Kick-start gatekeepers as separate step | Create a short 'Kick-start Assessment' phase containing only Tier1 gatekeepers across domains. After completion: show recommended path (Core/Standard/Deep) + override toggle. | Feels logical; reduces random jumping; sets expectations on scope/time. | Provides stable initial state for routing engine and progress metrics. | assessment.html flow + routing engine | None | New endpoint optional: /gatekeepers/list | New welcome flow steps | Users complete gatekeepers first; then enter main assessment with pruned path. | P0-01, P1-05 | M | Also improves low-maturity experience (clear start). | P1-06,P1,Enterprise Core,UX / IA,Kick-start gatekeepers as separate step,Create a short 'Kick-start Assessment' phase containing only Tier1 gatekeepers across domains. After completion: show recommended path (Core/Standard/Deep) + override toggle.,Feels logical; reduces random jumping; sets expectations on scope/time.,Provides stable initial state for routing engine and progress metrics.,assessment.html flow + routing engine,None,New endpoint optional: /gatekeepers/list,New welcome flow steps,Users complete gatekeepers first; then enter main assessment with pruned path.,P0-01, P1-05,M,Also improves low-maturity experience (clear start). | Not started
P1-07 | P1 | Enterprise Core | Low Maturity / Shadow | Shadow maturity capture pack | Add a small question pack to detect 'pockets of excellence' in otherwise low-maturity orgs (localized controls, strong teams). Include 'scale this' recommendations. | Avoids demoralizing all-red results; creates realistic roadmap and upsell path. | Improves signal quality; distinguishes low maturity from zero capability. | Excel question bank additions + scoring tags + recommendations | New questions and tags; update ingest | None | UI: show 'strength pockets' section in results | Low-maturity org can still show localized strengths; report includes scale actions. | P1-03 | L | Use evidence confidence to avoid false positives. | P1-07,P1,Enterprise Core,Low Maturity / Shadow,Shadow maturity capture pack,Add a small question pack to detect 'pockets of excellence' in otherwise low-maturity orgs (localized controls, strong teams). Include 'scale this' recommendations.,Avoids demoralizing all-red results; creates realistic roadmap and upsell path.,Improves signal quality; distinguishes low maturity from zero capability.,Excel question bank additions + scoring tags + recommendations,New questions and tags; update ingest,None,UI: show 'strength pockets' section in results,Low-maturity org can still show localized strengths; report includes scale actions.,P1-03,L,Use evidence confidence to avoid false positives. | Not started
P1-08 | P1 | Enterprise Core | Role Lenses | Role/Function dashboards (CISO / IA / HR views) | Add role views: filter questions and results by role packs; allow stakeholders to focus and collaborate. Tailor question wording/add-ons for IA & HR. | Improves completion and accuracy; increases adoption across org. | Enables multi-user later; supports modular content expansion. | assessment.html dashboard, question metadata (role tags), services.py filtering | Add role_tag to questions (already exists in bank map) and store per-response role | Optional: /questions/by_role | Dashboard toggle: Overall vs Role view | Role view shows only relevant domains/questions; report includes stakeholder appendices. | P1-05 | L | Start with view-only filtering; later add assignments. | P1-08,P1,Enterprise Core,Role Lenses,Role/Function dashboards (CISO / IA / HR views),Add role views: filter questions and results by role packs; allow stakeholders to focus and collaborate. Tailor question wording/add-ons for IA & HR.,Improves completion and accuracy; increases adoption across org.,Enables multi-user later; supports modular content expansion.,assessment.html dashboard, question metadata (role tags), services.py filtering,Add role_tag to questions (already exists in bank map) and store per-response role,Optional: /questions/by_role,Dashboard toggle: Overall vs Role view,Role view shows only relevant domains/questions; report includes stakeholder appendices.,P1-05,L,Start with view-only filtering; later add assignments. | Not started
P2-01 | P2 | Differentiators | Results | Risk heatmap + risk catalog | Define a risk catalog (e.g., IP leakage, privileged misuse, shadow AI exfil). Map question tags/axes patterns to risk likelihood/impact. Render heatmap in results and export. | Executives understand heatmaps; supports board reporting; accelerates advisory conversations. | Provides a stable taxonomy; supports integrations later. | engines.py (risk mapping), new risk_catalog data, assessment.html results | New risk definitions JSON/table; store top risks in snapshot | None | Heatmap + top risks list + drilldown | Heatmap reflects changes in answers; top risks have clear rationale and linked questions. | P1-04, P1-03 | L | Start with 10–15 risks; expand later. | P2-01,P2,Differentiators,Results,Risk heatmap + risk catalog,Define a risk catalog (e.g., IP leakage, privileged misuse, shadow AI exfil). Map question tags/axes patterns to risk likelihood/impact. Render heatmap in results and export.,Executives understand heatmaps; supports board reporting; accelerates advisory conversations.,Provides a stable taxonomy; supports integrations later.,engines.py (risk mapping), new risk_catalog data, assessment.html results,New risk definitions JSON/table; store top risks in snapshot,None,Heatmap + top risks list + drilldown,Heatmap reflects changes in answers; top risks have clear rationale and linked questions.,P1-04, P1-03,L,Start with 10–15 risks; expand later. | Not started
P2-02 | P2 | Differentiators | Optional Modules | Conditional regulatory / topical add-ons (not optional by default) | Implement add-on modules: Whistleblowing, IRM standards/laws, NIS2, DORA. Ask only when relevant (intake triggers) and when maturity suggests depth is useful. | Improves relevance; sells premium modules; avoids survey bloat. | Modular question selection; prevents irrelevant questions. | Excel bank + intake triggers + routing engine | Module flags in assessment context/snapshot | None | UI: module status + optional override to include | Modules appear only when triggered; can be enabled manually with explicit acknowledgment. | P1-05, P1-01 | M | Treat as separate packs with their own reporting sections. | P2-02,P2,Differentiators,Optional Modules,Conditional regulatory / topical add-ons (not optional by default),Implement add-on modules: Whistleblowing, IRM standards/laws, NIS2, DORA. Ask only when relevant (intake triggers) and when maturity suggests depth is useful.,Improves relevance; sells premium modules; avoids survey bloat.,Modular question selection; prevents irrelevant questions.,Excel bank + intake triggers + routing engine,Module flags in assessment context/snapshot,None,UI: module status + optional override to include,Modules appear only when triggered; can be enabled manually with explicit acknowledgment.,P1-05, P1-01,M,Treat as separate packs with their own reporting sections. | Not started
P2-03 | P2 | Differentiators | Coverage | IP risk coverage expansion | Add IP-focused controls: code repo access, contractor controls, data classification for trade secrets, exfil detection, M&A boundary controls, legal response readiness. | IP risk is a primary insider risk driver; increases business relevance. | Improves domain completeness and risk mapping. | Question bank + risk catalog | New questions/tags | None | UI: appears only if intake indicates IP-heavy org or via override | Report includes IP risk section and prioritized actions. | P2-01 | M | Also aligns to persona/risk taxonomy. | P2-03,P2,Differentiators,Coverage,IP risk coverage expansion,Add IP-focused controls: code repo access, contractor controls, data classification for trade secrets, exfil detection, M&A boundary controls, legal response readiness.,IP risk is a primary insider risk driver; increases business relevance.,Improves domain completeness and risk mapping.,Question bank + risk catalog,New questions/tags,None,UI: appears only if intake indicates IP-heavy org or via override,Report includes IP risk section and prioritized actions.,P2-01,M,Also aligns to persona/risk taxonomy. | Not started
P2-04 | P2 | Differentiators | Personas | Persona signals module | Introduce persona detection as hypotheses (not accusations): 'disgruntled admin', 'shadow innovator', 'departing engineer'. Add guidance on signals to monitor and safe mitigations. | Highly compelling to executives; improves program readiness. | Adds structured reasoning without needing sensitive data. | Question bank + reporting + risk catalog | Persona taxonomy JSON; store detected personas in snapshot | None | Results: persona cards with cautionary language | Persona suggestions are traceable to signals; output remains privacy-safe. | P2-01 | L | Keep it advisory; avoid stigmatizing individuals. | P2-04,P2,Differentiators,Personas,Persona signals module,Introduce persona detection as hypotheses (not accusations): 'disgruntled admin', 'shadow innovator', 'departing engineer'. Add guidance on signals to monitor and safe mitigations.,Highly compelling to executives; improves program readiness.,Adds structured reasoning without needing sensitive data.,Question bank + reporting + risk catalog,Persona taxonomy JSON; store detected personas in snapshot,None,Results: persona cards with cautionary language,Persona suggestions are traceable to signals; output remains privacy-safe.,P2-01,L,Keep it advisory; avoid stigmatizing individuals. | Not started
P2-05 | P2 | Differentiators | Integrations | Connector framework (metadata only) | Create connector interfaces (IdP, MDM, SIEM, DLP/CASB). Pull counts/timestamps/coverage%. Use to adjust evidence confidence and trigger targeted follow-ups. | Reduces self-report bias; strong enterprise differentiator. | Privacy-first integration; no documents or PII; future automation. | New integrations module + services.py + scoring engine | connector_snapshots table; store in snapshot | New endpoints: /connectors/status, /connectors/ingest (admin) | UI: optional 'connectors' page (pilot) | With connectors enabled, report shows 'verified via telemetry' confidence boost and follow-ups. | P0-07 | L | Start with manual CSV import to validate value before APIs. | P2-05,P2,Differentiators,Integrations,Connector framework (metadata only),Create connector interfaces (IdP, MDM, SIEM, DLP/CASB). Pull counts/timestamps/coverage%. Use to adjust evidence confidence and trigger targeted follow-ups.,Reduces self-report bias; strong enterprise differentiator.,Privacy-first integration; no documents or PII; future automation.,New integrations module + services.py + scoring engine,connector_snapshots table; store in snapshot,New endpoints: /connectors/status, /connectors/ingest (admin),UI: optional 'connectors' page (pilot),With connectors enabled, report shows 'verified via telemetry' confidence boost and follow-ups.,P0-07,L,Start with manual CSV import to validate value before APIs. | Not started
P2-06 | P2 | Differentiators | AI Assist | AI analysis add-on (cost staged) | Phase 1 (low cost): rules-based narrative summarizer using archetype + top risks + recs. Phase 2: LLM summary from structured outputs only. Phase 3: private deployment options. | Adds premium value; speeds advisory insights; compelling demos. | Keeps privacy by avoiding raw PII and avoiding document ingestion. | New ai_assistant service; report generator | Store ai_summary in snapshot | Optional endpoint /analysis/summary | Results: 'Executive narrative' section | AI summary is consistent, cites drivers, and never leaks sensitive data. | P1-03, P2-01 | L | Cost depends on usage; start with deterministic templates first. | P2-06,P2,Differentiators,AI Assist,AI analysis add-on (cost staged),Phase 1 (low cost): rules-based narrative summarizer using archetype + top risks + recs. Phase 2: LLM summary from structured outputs only. Phase 3: private deployment options.,Adds premium value; speeds advisory insights; compelling demos.,Keeps privacy by avoiding raw PII and avoiding document ingestion.,New ai_assistant service; report generator,Store ai_summary in snapshot,Optional endpoint /analysis/summary,Results: 'Executive narrative' section,AI summary is consistent, cites drivers, and never leaks sensitive data.,P1-03, P2-01,L,Cost depends on usage; start with deterministic templates first. | Not started
P2-07 | P2 | Differentiators | UI/Brand | Belfort Advisory theming + layout polish | Apply brand palette (#e8b373, #907054, #011E3D) and typography (Spartan headings, Montserrat body). Improve spacing, focus states, accessibility contrast. | Professional polish increases trust and conversion. | Improves usability and reduces perceived prototype feel. | assessment.html CSS + shared styles | None | None | Update CSS + ensure responsive behavior | All pages reflect brand; no contrast/accessibility regressions; feels enterprise-grade. | None | S | Keep a theme file to avoid editing many pages. | P2-07,P2,Differentiators,UI/Brand,Belfort Advisory theming + layout polish,Apply brand palette (#e8b373, #907054, #011E3D) and typography (Spartan headings, Montserrat body). Improve spacing, focus states, accessibility contrast.,Professional polish increases trust and conversion.,Improves usability and reduces perceived prototype feel.,assessment.html CSS + shared styles,None,None,Update CSS + ensure responsive behavior,All pages reflect brand; no contrast/accessibility regressions; feels enterprise-grade.,None,S,Keep a theme file to avoid editing many pages. | Not started
P2-08 | P2 | Differentiators | UI/Controls | Sidebar collapsible/stretchable | Add collapse button, width drag handle, remember preference in localStorage. | Supports different workflows (review vs answering). | Improves layout flexibility and mobile usability. | assessment.html | None | None | UI controls added | Sidebar can collapse and resize without breaking content; preference persists. | P0-01 | S | Combine with role view navigation. | P2-08,P2,Differentiators,UI/Controls,Sidebar collapsible/stretchable,Add collapse button, width drag handle, remember preference in localStorage.,Supports different workflows (review vs answering).,Improves layout flexibility and mobile usability.,assessment.html,None,None,UI controls added,Sidebar can collapse and resize without breaking content; preference persists.,P0-01,S,Combine with role view navigation. | Not started
P2-09 | P2 | Differentiators | UI/Review | Overview table page (domain x questions x answers) | Create a review page with a large table: question, selected answer, evidence confidence, marked/deferred flags, domain/axis tags. Export CSV. | Auditors love this; speeds internal review and sign-off. | Provides a deterministic artifact and reduces UI navigation complexity. | assessment.html new tab + API endpoint to fetch table view | None | GET /responses/table/{assessment_id} | New tab: Review Table | Table renders quickly and matches DB state; can export. | P0-02 | M | Later: add filters by role/domain/flag. | P2-09,P2,Differentiators,UI/Review,Overview table page (domain x questions x answers),Create a review page with a large table: question, selected answer, evidence confidence, marked/deferred flags, domain/axis tags. Export CSV.,Auditors love this; speeds internal review and sign-off.,Provides a deterministic artifact and reduces UI navigation complexity.,assessment.html new tab + API endpoint to fetch table view,None,GET /responses/table/{assessment_id},New tab: Review Table,Table renders quickly and matches DB state; can export.,P0-02,M,Later: add filters by role/domain/flag. | Not started
P3-01 | P3 | Scale | Auth/Multi-tenancy | Tenant isolation + RBAC + production auth | Introduce tenant table, tenant_key, RBAC (CISO/IA/HR). Replace dev auth with JWT/OIDC later. Add audit logs and revocation for assessment keys. | Required for real enterprise deployment and commercial sales. | Prevents cross-tenant leakage; supports multiple stakeholders. | auth.py, models.py, repositories/services, DB migrations | Add tenant_id to all fact tables; user table; audit log table | Auth endpoints + middleware | Login flow + org workspace | All data isolated by tenant; keys cannot access other tenants; RBAC enforced. | P0-04 | L | Keep dev bypass for local dev only. | P3-01,P3,Scale,Auth/Multi-tenancy,Tenant isolation + RBAC + production auth,Introduce tenant table, tenant_key, RBAC (CISO/IA/HR). Replace dev auth with JWT/OIDC later. Add audit logs and revocation for assessment keys.,Required for real enterprise deployment and commercial sales.,Prevents cross-tenant leakage; supports multiple stakeholders.,auth.py, models.py, repositories/services, DB migrations,Add tenant_id to all fact tables; user table; audit log table,Auth endpoints + middleware,Login flow + org workspace,All data isolated by tenant; keys cannot access other tenants; RBAC enforced.,P0-04,L,Keep dev bypass for local dev only. | Not started
P3-02 | P3 | Scale | Ops | Migrations + tests + feature flags | Adopt Alembic migrations; add golden tests for archetypes, scoring invariants, branching. Introduce feature flags for new engines. | Allows safe evolution without breaking pilots; supports regulated buyers. | Prevents schema drift and regression. | alembic/, tests.py, CI pipeline | Migration scripts | None | None | Fresh DB bootstrap succeeds; tests cover core logic; scoring changes are gated. | Stable milestone of P1 | L | Also helps manage question-bank version upgrades. | P3-02,P3,Scale,Ops,Migrations + tests + feature flags,Adopt Alembic migrations; add golden tests for archetypes, scoring invariants, branching. Introduce feature flags for new engines.,Allows safe evolution without breaking pilots; supports regulated buyers.,Prevents schema drift and regression.,alembic/, tests.py, CI pipeline,Migration scripts,None,None,Fresh DB bootstrap succeeds; tests cover core logic; scoring changes are gated.,Stable milestone of P1,L,Also helps manage question-bank version upgrades. | Not started
P3-03 | P3 | Scale | Reporting | Immutable snapshots + report generation pipeline | Finalize snapshot model: store bank hash, engine version, results JSON, recs, AI narrative. Add PDF/slide export later. | Board-ready artifacts drive program funding and advisory engagement. | Ensures results are reproducible even when bank updates. | models.py report_snapshots, services.py, export module | report_snapshots JSONB fields | POST /reports/generate, GET /reports/{id} | Download buttons in UI | Report exports match snapshot exactly; changing bank doesn't change old reports. | P1-03 | L | Start with HTML export, then PDF. | P3-03,P3,Scale,Reporting,Immutable snapshots + report generation pipeline,Finalize snapshot model: store bank hash, engine version, results JSON, recs, AI narrative. Add PDF/slide export later.,Board-ready artifacts drive program funding and advisory engagement.,Ensures results are reproducible even when bank updates.,models.py report_snapshots, services.py, export module,report_snapshots JSONB fields,POST /reports/generate, GET /reports/{id},Download buttons in UI,Report exports match snapshot exactly; changing bank doesn't change old reports.,P1-03,L,Start with HTML export, then PDF. | Not started

## README
IRMMF v6.1 — Program/Action Plan (generated)
Generated: 2026-01-11
How to use:
1) Filter by Priority (P0–P3) and Phase.
2) Sort by Workstream to assign owners.
3) Use Acceptance criteria as definition-of-done for tickets.
Key decisions embedded:
- Override depth is enabled in alpha; responses must be tagged origin=adaptive¦override.
- No 'Not Applicable' option for now.
- Evidence uses per-question micro-questions driven by templates keyed by evidence_policy_id (no file uploads).
- Archetype output is single primary result; keep internal runner-up for future without changing UI.
- Benchmarking: support external peer groups later; intake remains anonymous.
- Connectors: metadata-only stage 1; used for confidence and follow-ups, not raw scoring initially.